## WBS
WBS ID | 업무구분 |  |  |  |  | 책임자 | 2019.11 | [19 empty] | 2019.12
[6 empty] | 김영규 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
김준
박상철
SM10000 | SportsMatching
SM11000 | 요구분석
요구사항수집 | bar: 2019.11 11 to 2019.11 12
요구분석서 작성 | bar: 2019.11 13 to 2019.11 14; 2019.11 18 to 2019.11 19
유스케이스 작성 | bar: 2019.11 20 to 2019.11 21
수정 및 승인 | bar: 2019.11 21
계획
FBS작성 | bar: 2019.11 21
WBS작성 | bar: 2019.11 21 to 2019.11 22
수정 및 승인 | bar: 2019.11 22
설계
설계
DB 설계
데이터베이스 구조 설계 | bar: 2019.11 23
데티어베이스 정규화 | bar: 2019.11 23 to 2019.11 24
ERD작성 | bar: 2019.11 24 to 2019.11 25
쿼리 테스트 | bar: 2019.11 25 to 2019.11 27
UI/UX 설계
UX설계
수정 및 승인
스프링 구조 설계
스프링 기본 템플릿 세팅 | bar: 2019.11 27
공통 모듈 설계 | bar: 2019.11 27
개발환경 구축
개발 도구 설치 및 교육 | bar: 2019.11 28
소스 코드 관리 / 통합 빌드 환경 구축 | bar: 2019.11 28
개발서버(WAS, DB) 구축 | bar: 2019.11 28
이슈관리/버그추적 환경 구축 | bar: 2019.11 28
네비게이션 흐름도 작성
|  |  | 회원관리 |  |  | 박상철 | bar: 2019.11 29
|  |  | 구장관리 |  |  | 김준 | bar: 2019.11 29
|  |  | 일정관리 |  |  | 김영규 | bar: 2019.11 29
|  |  | 매칭관리 |  |  | 김준 | bar: 2019.11 29
|  |  | 채팅 |  |  | 김영규 | bar: 2019.11 29
|  |  | 지도 |  |  | 김영규 | bar: 2019.11 29
기능구현
회원관리
회원가입
개인회원 회원가입
[5 empty] | API로 최초 로그인 시 아이디를 DB에 저장 | 박상철
팀 창단(팀 회원가입)
[5 empty] | 팀 아이디, 팀 비밀번호, 대표 연락처, 대표 아이디를 입력받아 DB에 저장 | 박상철
[5 empty] | 팀 아이디 중복검사 | 박상철
[5 empty] | 비밀번호 정규화 | 박상철
로그인 / 로그아웃
로그인
[5 empty] | 로그인 시 세션에 정보 등록 | 박상철
[5 empty] | 중복 로그인 검사 | 박상철
로그아웃
[5 empty] | 로그아웃 시 세션에 정보 삭제 | 박상철
회원정보수정
팀 정보 수정
[5 empty] | 대표 아이디 수정 | 박상철
[5 empty] | 대표 연락처 수정 | 박상철
[5 empty] | 비밀번호 수정 | 박상철
개인 회원 정보 수정
[5 empty] | 소속팀 수정 | 박상철
관리자 정보 수정
[5 empty] | 비밀번호 수정 | 박상철
회원정보조회
팀 조회
[5 empty] | 팀 이름 클릭시 팀에 대한 정보 출력 (팀 통계정보 포함) | 김준
개인 회원 조회
[5 empty] | 마이페이지 클릭시 개인 회원에 대한 정보 출력 | 박상철
팀원 조회
[5 empty] | 팀원 아이디로 팀원 정보 검색 | 박상철
회원탈퇴
개인회원의 팀 탈퇴
[5 empty] | 개인회원 정보에서 팀 정보 삭제 | 박상철
개인회원의 탈퇴
[5 empty] | DB에서 개인회원정보 삭제 | 박상철
[5 empty] | 팀의 소속된 팀원정보 삭제 | 박상철
구장관리
구장 조회
사용자의 구장조회
[5 empty] | 지역이름으로 구장 검색 | 김준
[5 empty] | 구장명으로 구장 검색 | 김준
[5 empty] | 구장정보 조회 | 김준
관리자의 구장조회
[5 empty] | 구장 전체 조회 | 김준
[5 empty] | 구장 상세 조회 (구장 통계정보 포함) | 김준
구장 수정
구장 정보 수정
[5 empty] | 기존 값에서 변경된 값 수정 | 김준
구장 운영시간 수정
[5 empty] | 구장 운영 시간 수정 | 김준
구장 삭제
관리자의 구장 삭제
[5 empty] | DB에서 구장 삭제 | 김준
진행되지 않은 예약정보 존재여부 확인
Session에 담긴 로그인 정보와 입력된 아이디/비밀번호 비교확인
구장 등록
관리자의 구장 등록
[5 empty] | 구장명, 위치, 면적,사진을 받아 DB에 저장 | 김준
사진 입력 시 미리보기 기능
일정관리
일정 등록
사용자 일정 등록
[5 empty] | 원하는 시간에 등록요청(승인여부 null->N) | 김영규
관리자 일정 등록
등록요청받으면 해당 경기일정 등록(등록여부 N->Y)
일정 삭제
사용자 일정 취소
[5 empty] | 예약한 일정만 취소요청(취소여부null->N) | 김영규
관리자 일정 취소
[5 empty] | 취소요청을 승인하면 해당 경기일정 삭제(취소여부 N->Y) | 김영규
알림
[5 empty] | 취소한 경기 알림 | 김영규
일정 조회
전체 일정 조회
[5 empty] | 캘린더에서 선택한 날의 모든 경기 일정 조회 | 김영규
상세 일정 조회
[5 empty] | 선택한 시간의 경기 일정 조회 | 김영규
매칭관리
매칭 조회
매칭 전체조회
[5 empty] | 등록되어있는 모든 매칭카드 조회 | 김준
출력화면 페이징처리
매칭 검색
[5 empty] | 주 활동지를 통해 검색 | 김준
팀 명을 통해 검색
경기방식을 통해 검색
출력화면 페이징처리
매칭 상세조회
[5 empty] | 소속 팀의 모든 매칭내역 조회 | 김준
출력화면 페이징처리
매칭 등록
매칭카드 등록
[5 empty] | 신규 매칭카드 등록 | 김준
매칭 신청
[5 empty] | 매칭카드를 등록한 팀에게 매칭 신청 | 김준
이미 신청된 매칭 수 검토 (최대 3개)
매칭 성사
[5 empty] | 매칭이 성사되면 해당 매칭을 성사된 매칭으로 복사 | 김준
매칭카드의 해당 매칭은 성사여부를 'Y'로 변경
매칭 삭제
매칭카드 삭제
[5 empty] | 소속 팀의 매칭카드 중 매칭신청이 없고 성사되지 않은 매칭카드 삭제 | 김준
매칭신청 삭제
[5 empty] | 아직 수락되지 않은 매칭신청에 한해 신청 삭제 | 김준
매칭내역 수정
매칭내역 수정
[5 empty] | 소속 팀의 지난 매칭내역 정보 수정 | 김준
소속 팀의 다가올 매칭내역 정보 수정
채팅
채팅방 생성
|  |  |  | 대화내역 불러오기 |  | 김영규
|  |  |  | 채팅방 참가회원 목록 출력 |  | 김영규
메시지 전송
|  |  |  | 전송 버튼과 엔터로 메시지 전송 |  | 김영규
채팅방 조회
|  |  |  | 전체 목록 출력 |  | 김영규
|  |  |  | 선택한 목록 출력 |  | 김영규
채팅방 삭제
|  |  |  | 선택한 채팅방 삭제 |  | 김영규

## 구장관리
구분 | 기능 |  | 쿼리 | 명명(ID) | argument(Paramter) | return(Result) | 비고
구장관리 | 사용자 조회 | 구장검색 | SELECT STADIUM_CODE, STADIUM_NAME, ADDRESS FROM STADIUM WHERE SI_GUN_GU = '' SELECT STADIUM_CODE, STADIUM_NAME, ADDRESS FROM STADIUM WHERE STADIUM_NAME = '' | searchStadium
|  | 구장 상세조회 | SELECT ADDRESS, AREA, INFO, P.IMAGE1, P.IMAGE2, P.IMAGE3 FROM STADIUM S JOIN PICTURE P ON S.STADIUM_CODE = P.STADIUM_CODE WHERE S.STADIUM_CODE = '' | selectDetailStadium
| 관리자 조회 | 내 구장 조회 | SELECT STADIUM_CODE, STADIUM_NAME FROM STADIUM WHERE ADMIN_ID = '' | selectMyStadium
|  | 내 구장 상세조회 | SELECT S.STADIUM_CODE, STADIUM_NAME, ADDRESS, AREA, INFO, P.IMAGE1, P.IMAGE2, P.IMAGE3 FROM STADIUM S JOIN PICTURE P ON S.STADIUM_CODE = P.STADIUM_CODE WHERE S.ADMIN_ID = '' | selectMyDetailStadium
| 수정 | 구장 정보수정 | UPDATE STADIUM SET STADIUM_NAME='', AREA='', SI_GUN_GU='', ADDRESS='', INFO='' WHERE STADIUM_CODE =''; UPDATE PICTURE SET IMAGE1='', IMAGE2='', IMAGE3='' WHERE STADIUM_CODE =''; | modifyStadiumInfo
| 삭제 | 진행되지 않은 예약정보 확인 | SELECT COUNT(*) FROM SCHEDULE WHERE STADIUM_CODE ='' AND GAME_DATE > SYSDATE; | selectReservationInfo
|  | 관리자 로그인 | SELECT ADMIN_ID FROM STADIUM_ADMIN WHERE ADMIN_ID = '' AND ADMIN_PW = ''; | adminLogin
|  | 구장 삭제 | DELETE FROM STADIUM WHERE STADIUM_CODE=''; | deleteStadium
| 등록 | 구장 등록 | INSERT INTO STADIUM VALUES( (SELECT SUBSTR(MAX(STADIUM_CODE), 0, 2) ¦¦ TO_CHAR(SUBSTR(MAX(STADIUM_CODE), 3)+1, 'FM0000') FROM STADIUM) ,'','','','','','') | registStadium

## 매칭관리
구분 | 기능 |  | 쿼리 | 명명(ID) | argument(Paramter) | return(Result) | 비고
매칭관리 | 매칭 조회 | 매칭 전체조회 | SELECT M.APPLIED_TEAM_ID, T.PLAYGROUND, T.STAT, M.RESERVATION_STADIUM, M.MATCHING_STYLE, M.APPLIED_TEAM_INFO FROM MATCHING_CARD M JOIN TEAM T ON M.APPLIED_TEAM_ID = T.TEAM_ID | selectAllMatching | - | DTO
|  | 매칭 검색 | SELECT MC.GAME_DATE, MC.APPLIED_TEAM_ID, MC.RESERVATION_STADIUM, MC.MATCHING_STYLE, SM.COMMENTS FROM (SCHEDULED_MATCHING SM JOIN MATCHING_CARD MC ON SM.MATCHING_NUMBER = MC.MATCHING_NUMBER) JOIN TEAM T ON MC.REGIST_TEAM_ID = T.TEAM_ID WHERE T.PLAYGROUND LIKE '%1%' OR MC.REGIST_TEAM_ID LIKE '%1%' OR MC.MATCHING_STYLE LIKE '%1%' | searchMatching | String playground or team_id or matchingStyle | DTO | 다이나믹쿼리
|  | 내 매칭내역 조회 | SELECT MC.MATCHING_NUMBER, MC.GAME_DATE, MC.APPLIED_TEAM_ID, MC.RESERVATION_STADIUM, MC.MATCHING_STYLE, SM.COMMENTS FROM SCHEDULED_MATCHING SM JOIN MATCHING_CARD MC ON SM.MATCHING_NUMBER = MC.MATCHING_NUMBER WHERE MC.REGIST_TEAM_ID = '' OR MC.APPLIED_TEAM_ID = '' | selectMyMatching | String team_id | DTO
| 매칭 등록 | 매칭카드 등록 | INSERT INTO MATCHING_CARD VALUES (MATCHING_SEQ.NEXTVAL,'','','','','','','') | registMatchingCard | DTO | -
|  | 매칭신청 | UPDATE MATCHING_CARD SET APPLIED_TEAM_ID='', APPLIED_TEAM_INFO='' WHERE MATCHING_NUMBER='' | applyMatching | Map | - | 다이나믹쿼리
|  | 기존 매칭 수 조회 | SELECT COUNT(*) FROM MATCHING_CARD WHERE APPLIED_TEAM_ID ='' AND ACCOMPLISH ='N' |  | - | String team_id
|  | 매칭성사여부 수정 | UPDATE MATCHING_CARD SET ACCOMPLISH='Y' WHERE MATCHING_NUMBER='' |  | Integer | -
|  | 성사된 매칭 등록 | INSERT INTO SCHEDULED_MATCHING VALUES ('','','','') | selectMatchingCount | DTO | -
| 매칭 삭제 | 매칭카드 삭제 | DELETE FROM MATCHING_CARD WHERE MATCHING_NUMBER='' | deleteMatchingCard | Integer | -
|  | 매칭신청 여부 조회 | SELECT APPLIED_TEAM_ID FROM MATCHING_CARD WHERE MATCHING_NUMBER='' |  | Integer | String team_id
|  | 매칭신청 삭제 | UPDATE MATCHING_CARD SET APPLIED_TEAM_ID = NULL, APPLIED_TEAM_INFO=NULL WHERE MATCHING_NUMBER='' AND ACCOMPLISH='N' | deleteApplyMatching | Integer | -
| 매칭내역 수정 | 지난 매칭내역 정보 수정 | UPDATE SCHEDULED_MATCHING SET COMMENTS='' WHERE MATCHING_NUMBER='' | modifyMatchingHistory | Map | -
|  | 다가올 매칭내역 정보 수정 | UPDATE MATCHING_CARD SET MATCHING_STYLE='', RESERVATION_STADIUM='' WHERE MATCHING_NUMBER='' | modifyNearMatching | Map | -

## 일정관리
구분 | 기능 |  | 쿼리 | 명명(ID) | argument(Paramter) | return(Result) | 비고
일정관리 | 일정등록 | 관리자 일정등록 | INSERT INTO SCHEDULE(SCHEDULE_ID, STADIUM_CODE, GAME_DATE) VALUES(SCHEDULE_SEQ.NEXTVAL,#{stadium_code}, #{game_date}); | registerSchedule | DTO | boolean
|  | 홈팀 일정등록 | UPDATE SCHEDULE SET HOME_RESERVATION = 'N' WHERE SCHEDULE_ID = #{schedule_id}; | homeRegisterSchedule | Integer | boolean
|  | 홈팀 최종등록 | UPDATE SCHEDULE SET HOME_RESERVATION = 'Y', HOME_TEAM = #{team_id} WHERE SCHEDULE_ID = #{schedule_id}; | homeConfirmSchedule | DTO | boolean
|  | 어웨이팀 일정등록 | UPDATE SCHEDULE SET AWAY_RESERVATION = 'N' WHERE SCHEDULE_ID = #{schedule_id}; | awayRegisterSchedule | Integer | boolean
|  | 어웨이팀 최종등록 | UPDATE SCHEDULE SET AWAY_RESERVATION = 'Y', AWAY_TEAM = #{team_id} WHERE SCHEDULE_ID = #{schedule_id}; | awayConfirmSchedule | DTO | boolean
| 일정삭제 | 홈팀 일정취소 | UPDATE SCHEDULE SET HOME_CANCEL = 'N' WHERE SCHEDULE_ID = #{schedule_id}; | homeCancel | Integer | boolean
|  | 홈팀 최종취소 | UPDATE SCHEDULE SET HOME_CANCEL = '', HOME_RESERVATION = '', HOME_TEAM = '' WHERE SCHEDULE_ID = #{schedule_id}; | homeCancelConfirm | Integer | boolean
|  | 어웨이팀 일정취소 | UPDATE SCHEDULE SET AWAY_CANCEL = 'N' WHERE SCHEDULE_ID = #{schedule_id}; | awayCancel | Integer | boolean
|  | 어웨이팀 최종취소 | UPDATE SCHEDULE SET AWAY_CANCEL = '', AWAY_RESERVATION = '', AWAY_TEAM= '' WHERE SCHEDULE_ID = #{schedule_id}; | awayCancelConfirm | Integer | boolean
|  | 일정 삭제 | DELETE FROM SCHEDULE WHERE SCHEDULE_ID = #{schedule_id}; | deleteSchedule | Integer | boolean
| 일정조회 | 사용자 일정 조회 | SELECT NVL(HOME_TEAM,'홈팀 없음'), NVL(AWAY_TEAM, '어웨이팀 없음') FROM SCHEDULE WHERE GAME_DATE = #{game_date}; | selectSchedule | Date | Dto

## 회원관리
구분 | 기능 |  | 쿼리 | 명명 | Argument | return | 비고
회원관리 | 회원 | 회원조회 | SELECT MEMBER_ID FROM MEMBERS | selectMember
|  | API로그인 | INSERT INTO MEMBERS (MEMBER_ID) VALUES(#{member_id}); | apiLogin
|  | 회원탈퇴 | DELETE FROM MEMBERS WHERE MEMBER_ID= #{member_id} | memberWithdraw
| 팀 | 팀 회원 가입 | INSERT INTO TEAM (TEAM_ID, TEAM_PW, CAPTAIN_ID, CAPTAIN_PHONE_NUMBER, PLAYGROUND, QUESTION, ANSWER, DORMANT_ID) VALUES(#{team_id}, #{team_pw}, #{captain_id}, #{captain_phone_number}, #{playground}, #{question}, #{answer}, #{dormant_id}) | teamRegist
|  | 팀 로그인 | SELECT TEAM_ID FROM TEAM WHERE TEAM_ID = #{team_id} AND TEAM_PW = #{team_pw} | teamLogin
|  | 팀 아이디 중복검사 | SELECT COUNT(TEAM_ID) FROM TEAM WHERE TEAM_ID = #{team_id} | teamDuplicateId
|  | 팀 조회 | SELECT TEAM_ID, TEAM_PW, CAPTAIN_ID, CAPTAIN_PHONE_NUMBER, PLAYGROUND, QUESTION, ANSWER, DORMANT_ID FROM TEAM | selectTeam
|  | 팀 정보 수정 | UPDATE TEAM SET TEAM_PW= #{team_pw}, CAPTAIN_ID= #{captain_id}, CAPTAIN_PHONE_NUMBER= #{captain_phone_number}, PLAYGROUND= #{playground}, QUESTION= #{question}, ANSWER= #{answer}, DORMANT_ID= #{dormant_id} WHERE TEAM_ID= #{team_id} | modifyTeamInfo
|  | 팀 삭제 | DELETE FROM TEAM WHERE TEAM_ID= #{team_id} | deleteTeam
| 소속팀 | 소속팀 조회 | SELECT BELONGED_TEAM_CODE FROM BELONGED_TEAM WHERE MEMBER_ID = #{member_id} AND TEAM_ID = #{team_id} | selectBelongedTeam
|  | 소속팀 수정 | UPDATE BELONGED_TEAM SET BELONGED_TEAM_CODE = #{belonged_team_code} WHERE MEMBER_ID = #{member_id} AND TEAM_ID = #{team_id} | modifyBolongedTeam
| 관리자 | 관리자 로그인 | SELECT ADMIN_ID FROM STADIUM_ADMIN WHERE ADMIN_ID = #{admin_id} AND ADMIN_PW = #{admin_pw} | adminLogin
|  | 관리자 비밀번호 수정 | UPDATE STADIUM_ADMIN SET ADMIN_PW= #{admin_pw} WHERE ADMIN_ID= #{admin_id} | modifyAdminPw

## 채팅
구분 | 기능 |  | 쿼리 | 명명(ID) | argument(Paramter) | return(Result) | 비고
채팅 | 채팅방 생성 | 관리자 채팅방 생성 | INSERT INTO ADMIN_CHATTING(CHAT_ID, CHATTER1, CHATTER2, DELFLAG) VALUES(ADMIN_CHAT_SEQ.NEXTVAL, #{admin_id}, #{member_id}, 'N'); | createAdminChatting | Dto | boolean
| 메시지 전송 | 관리자와 사용자 간 메시지 전송 | INSERT INTO ADMIN_MESSAGE(CHAT_ID, MSG_CHAT_ID, MESSAGE_CONTENT, MESSAGE_DATE, SENDER) VALUES((SELECT CHAT_ID FROM ADMIN_CHATTING WHERE CHATTER1 = #{admin_id} AND CHATTER2 =#{member_id}) ,ADMIN_MSG_SEQ.NEXTVAL, #{content}, SYSDATE, #{session_id}); | sendAdminMessage | Dto | boolean
| 채팅방 체크 | 채팅방이 생성되어있는지 체크 | SELECT COUNT(*) FROM ADMIN_CHATTING WHERE CHATTER1 = #{admin_id} AND CHATTER2 =#{member_id} | checkChatting | String | Integer
| 채팅방 조회 | 채팅방을 조회 | SELECT MESSAGE_CONTENT, MESSAGE_DATE FROM ADMIN_MESSAGE WHERE CHAT_ID = (SELECT CHAT_ID FROM ADMIN_CHATTING WHERE (#{member_id}) IN (CHATTER1, CHATTER2)); | selectChatting | String | Dto